## Introduction
Earned Value Management Software Buyers Guide Worksheets
The following worksheets are meant to provide a place to start to help you define your business and functional requirements. It is intended to help you organize your requirements and gather fact-based information to determine which earned value management (EVM) software tool best meets your needs.
The example worksheets include:
Business Requirements
Required Functionality
Deployment Environment
For more information about ProjStream, visit www.projstream.com.
© 2023 ProjStream LLC, Revision August 22, 2023

## Business Requirements
Business Requirements
Ref. No.
1 | Issue | Government contracts the company is bidding on require EVM performance reporting or an EIA-748 compliant EVMS to be in place. This means updating processes and procedures along with implementing new tools to support the contractual requirements.
|  | Current State | Process and procedures need to be updated to incorporate EVM best practices. Lack a cost management tool to manage the complete set of time phased cost data (budget, earned value, actual cost, estimate to complete (ETC), and estimate at completion (EAC)) to calculate performance metrics.
|  | Requirement | Establish a central EVM database for project teams to maintain budget, earned value, actual cost, ETC, and EAC data that integrates with the schedule tool. Tool should provide a collaborative working environment where all team members can manage and view the data as well as track changes
|  | Expected Outcome | Single authoritative source for the EVM data to produce data views and performance reports with confidence. Can produce ad-hoc reports as well as contractual reporting deliverables. Can demonstrate full data traceability, independently verify project manager produced range of EACs.
2 | Issue | Project start up after contract award is taking too long and impacts the ability to be prepared for an Integrated Baseline Review (IBR). Need means to leverage the proposal schedule, cost estimate, and basis of estimate (BOE) to quickly create an executable performance measurement baseline (PMB).
|  | Current State | Proposal and project execution functions are siloed. Business development produces ad-hoc Excel spreadsheets for proposals that lack substantiation. Project control teams must start over at contract award.
|  | Requirement | Establish a central cost estimating and EVM database where proposal teams hand-off proposal schedule and cost estimating data with rationale to project control teams after contract award. Resource loaded schedule activities provide the source data for the time phased budget.
|  | Expected Outcome | Goal is to reduce project start up duration by 80% by removing process silos. Significant improvement in the quality of the schedule and cost data as project control teams can use the integrated source data with rationale from the proposal phase as the basis to produce the PMB.
3 | Issue | The government customer has issued a number of EVMS corrective action requests (CARs) related to schedule and cost data quality issues. The in-house developed cost management software is unable to scale to support the performance management requirements, lacks means to integrate with the schedule tool.
|  | Current State | Legacy software tool is unable to provide the necessary data to support the EVMS. Project control teams lack the means to integrate the schedule and cost data. Project managers lack the tools needed to manage the complete set of time phased cost data, produce EVM metrics, identify and analyze significant variances, as well as produce a range of EACs for performance reporting.
|  | Requirement | Establish a single cost management tool as a central database to maintain the time phased cost data. The tool must support standard methods for measuring work performance and calculate standard EVM metrics that can be analyzed in an interactive dashboard. The schedule and cost tools must be integrated to create schedule driven budget and ETC data with schedule status as the basis for claiming earned value.
|  | Expected Outcome | Incrementally improve data quality over the next six months to meet the milestones in corrective action plans (CAPs). Enhanced process will ensure schedule and cost data alignment. Reduce time spent performing manual data quality data checks by 80%. Eliminate use of ad-hoc macros used to supplement the current tool. Reduce time to prepare, validate, and submit customer performance reports by 65%.
4 | Issue
Current State
Requirement
Expected Outcome
Notes:
Identify how you intend to measure the impact of an issue in time or cost. Use the same measure to quantify the expected outcome by eliminating or reducing the impact of the issue. Use this data to calculate the return on investment and how quickly results can be achieved.

## Required Functionality
Required Functionality
Category | Functionality | Rating | Tool A | Tool B | Notes/Comments
Configuration, Setting Up Core Data
| Can establish a standard accounting calendar template | Required | Yes | Yes
| Projects can define specific reporting calendars as well as resource calendars | Required
| Can establish a standard base project configuration new projects can use as a template to enable cross-project reporting and analysis | Required
| Can create an unlimited number of user defined code lists and structures, add a variety of different types of user defined fields (text, codes, flags, Boolean, dates) to support project unique data views and reporting requirements | Required
| Can establish a standard rate template and rate calculations with ability to create custom expressions | Required
| Can build complex rate structures with ability to apply escalation factors | Required
| Can create an unlimited number of rate structures for different cost types (budget, actual costs, estimates) | Required
| Can import current rates from the accounting system | Required
| Can establish a standard hierarchical resource structure template with element of cost categories (labor, material, travel, other direct costs, subcontract) for IPMR or IPMDAR reporting | Required
| Can easily import data from other systems using Excel | Required
Planning
Build WBS structure
Import WBS from Excel
Import WBS from scheduling system (identify specific tools such as Microsoft Project or Oracle Primavera P6)
Can produce a WBS dictionary
Can parse statement of work (SOW) document paragraphs into a code structure to map to WBS elements
Means to identify control accounts and summary level planning packages (SLPPs)
Control accounts can be at any level within the WBS (project defined)
Budgeting
Easy to use grid view similar to Excel to enter data with built-in hierarchical structure to view the data at summary, intermediate, and detail levels
Ability to change the order of the columns, hide or show columns, sort and filter the data in the grid view similar to Excel
Project team members can collaborate and share the cost data with optional user locks
Ability to import proposal cost estimate and basis of estimate (BOE) rationale as the initial basis for the time phased budget
Can enter budgets in hours, full time equivalents (FTEs), or cost and select the rate structure to apply direct and indirect rates
Can create custom budget distribution spreads and learning curves
Import resource loaded activity data from scheduling system to produce the time phased budget data
Ability to enter BOE, SOW, and other text documentation with the budget data at user determined level of detail
Can create hierarchical bills of material (BOM) and assign material categories
Supports standard EVM techniques: 0/100, 100/0, 50/50, User Defined, Percent Complete, Earning Rules, Milestones, LOE, and Apportioned Effort
Supports rolling wave planning techniques
Built-in contract budget base (CBB) log to track the CBB, management reserve (MR), undistributed budget (UB), and distributed budget with monthly summary values as well as detailed transaction source data for historical traceability and internal audits
Ability to define additional budget cost codes to support various project scenarios such as an Over Target Baseline (OTB)
Measuring Performance
Import schedule activity status as the basis for the work package performance claimed in the cost tool
Ability to enter quantifiable backup data to substantiate the earned value claimed in the cost tool
Import actual costs from accounting system on a weekly and monthly basis
Enter estimated actuals for materials and subcontractors to align earned value claimed and actual costs in the same accounting month
Analyzing Performance
Variance thresholds can be set at any level in the WBS, can set both value and percent thresholds
Built-in cost data validation analysis view and report to identify common data anomalies
Import resource loaded activity data from scheduling system to produce the time phased estimate to complete (ETC) data
Web option for technical users or teaming partners to enter time phased ETC data or progress data
Ability to do what-if analysis and create different ETC scenarios
Ability to enter or calculate an unlimited range of estimates at completion (EACs)
Calculates standard EVM metrics
Reporting
Built-in ad-hoc and pivot table reporting, built-in report wizard
Built-in standard EVM reports (RAM, CAP, VAR), line charts and graphs with interactive dashboard to view, summarize, and drill down into the data for root cause analysis
Build-in standard IPMR Formats (1 to 5 and 7) and XML deliverable as well as IPMDAR Contract Performance Dataset (CPD) JSON encoded deliverable, Performance Narrative Report
Can produce ad-hoc data exports to support DCMA data calls
Single project, multi-project, or enterprise level portfolio analysis reporting
Workflow, Managing Changes
Ability to define user roles, routing rules and workflow queue to manage the development, entry, and maintenance of project data
Workflow available in the web to identify responsible parties for ETC or progress entry
Ability to manage baseline change requests, capture change rationale and impact analysis documentation, track to closure
Ability to manage work authorization forms
Approved baseline change requests automatically update work authorization forms and budget log, can track changes down to reference date, work package, and resource (element of cost)

## Deployment Environment
Deployment Environment
Security Requirements | Tool A | Tool B | Notes/Comments
SaaS subscription option available that is compliant with FedRAMP security requirements?
User access controls: Project level
User access controls: Role-based or user locking at WBS element level
User access controls: Subcontractor (external entity) specific grid view to enter or update data for specific WBS elements
Environment Details, Support Requirements |  |  | Notes/Comments
List other information the software vendor will need to price the software or to gain an understanding of likely costs you may incur to support the tool over time. Examples follow.
One or multiple locations? How many users at each location?
How many projects? What is the complexity and duration of the projects? Can the tool scale to support the smallest as well as the largest projects you have?
Single database?
What is built into the tool or are add-ons required? Do you need to purchase additional tools or utilities from the vendor to be able to meet your requirements?
What is the average release cycle for updates?
What is the average response and resolution time for software issues?
Does the software architecture support web services?
How easy is it to exchange data with other business systems?
How configurable is the tool?